## Cover
FINDINGS REGISTER & 90-DAY REMEDIATION ROADMAP
SOC 2 Type 1 Readiness Assessment
Client (Simulated): | MeridianHealth Analytics Pty Ltd
Engagement: | MHA-SOC2-2026-001
Total Findings: | 22 (4 High, 18 Medium, including informational Lows)
Remediation Window: | 90 days (29 April 2026 – 28 July 2026)
Sprint Cadence: | 6 two-week sprints
Prepared By: | Gaurav Govind, GRC Analyst
Date: | 28 April 2026
Version: | 1.0 — Final
Classification: | Confidential — Client
WORKBOOK CONTENTS
Cover | This sheet
Findings Register | All 22 findings with severity, owner, effort, target date, status
90-Day Roadmap | Sprint-by-sprint sequencing of remediation
Effort Summary | Effort metrics by severity, owner, and sprint (formulas)
Status Tracker | Tracking template for remediation progress

## Findings Register
Finding ID | Control Ref | Finding Title | Severity | CC | Description | Recommendation | Owner | Effort (days) | Sprint | Target Date | Status
F-001 | CC1.4-02 | Incomplete security awareness training & no phishing simulation | High | CC1 | KnowBe4 deployed but completion at 78% (target 100%); phishing simulation feature not enabled. | Drive completion to 100% before audit period; enable monthly phishing simulations; retain per-user evidence. | CISO | 5 | Sprint 1 | 31 March 2026 | Open
F-002 | CC2.3-02 | No defined customer incident notification SLA | High | CC2 | MSA references 'reasonable timeframes' rather than a contractual SLA; US healthcare clients expect 72-hour notice. | Define and contractually commit to 72-hour incident notification SLA; update MSA template; communicate to existing customers. | CISO / General Counsel | 8 | Sprint 1 | 31 March 2026 | Open
F-003 | CC6.2-01 | Annual access reviews fall short of SOC 2 audit expectation | High | CC6 | Production AWS, Okta, GitHub, and database access reviewed annually; SOC 2 audit pattern is quarterly with retained manager sign-off. | Move to quarterly access reviews; build manager sign-off workflow in Vanta or ServiceNow; retain evidence. | CISO / People & Culture | 10 | Sprint 1 | 31 March 2026 | Open
F-004 | CC9.2-04 | No CUEC tracker for sub-service organisations | High | CC9 | AWS, Okta, Datadog SOC 2 reports collected but Complementary User Entity Controls not formally mapped or tracked. | Build CUEC tracker mapping each sub-service organisation user-entity-control consideration to a MeridianHealth control; review on each new SOC report. | CISO | 6 | Sprint 1 | 31 March 2026 | Open
F-005 | CC1.2-01 | No Board-level Information Security Charter | Medium | CC1 | Quarterly security update on Board agenda since Q3 FY24, but no documented Board-level Security Charter or Risk Appetite Statement. | Draft and adopt a Board-approved Information Security Charter and Risk Appetite Statement aligned with US assurance expectations. | CISO / Board Secretary | 4 | Sprint 2 | 14 April 2026 | Open
F-006 | CC2.3-01 | No customer-facing Trust Centre | Medium | CC2 | MSA includes generic security clauses; no customer-facing Trust Centre or security commitments page. | Build customer-facing Trust Centre publishing SOC 2 status, ISO 27001 certificate, and incident notification commitments. | CISO / Marketing | 12 | Sprint 3 | 28 April 2026 | Open
F-007 | CC3.2-02 | No formal fraud risk assessment | Medium | CC3 | No formal fraud risk assessment documented; fraud risk covered informally by Finance. | Conduct an annual fraud risk assessment covering financial, operational, and IT-fraud scenarios; document and link to risk register. | CFO / CISO | 6 | Sprint 2 | 14 April 2026 | Open
F-008 | CC4.1-01 | No independent internal audit function | Medium | CC4 | Internal audit performed by CISO team annually; not independent of management. | Engage external internal-audit provider for FY26; alternatively rotate auditor across leadership. | CISO / Audit Committee | 8 | Sprint 4 | 12 May 2026 | Open
F-009 | CC5.3-01 | Stale policies awaiting review | Medium | CC5 | Four policies (DLP, Cryptography, Mobile Device, Acceptable Use) are over 24 months old without review. | Refresh stale policies; implement annual policy review cadence; adopt Vanta or Drata acknowledgement workflow. | CISO | 10 | Sprint 2 | 14 April 2026 | Open
F-010 | CC5.3-02 | Segregation of Duties not formally documented | Medium | CC5 | Production deployment requires peer review in GitHub; SoD not formally documented across deployment, access, and financial approvals. | Document SoD matrix covering deployment, access provisioning, and financial approvals; review quarterly. | CTO / CISO | 5 | Sprint 3 | 28 April 2026 | Open
F-011 | CC6.1-03 | No PAM tool for OS-level admin access | Medium | CC6 | AWS admin via IAM Identity Center with break-glass; no PAM tool for OS-level admin on EC2. | Implement Teleport or AWS Systems Manager Session Manager for OS-level access with session recording. | Security Engineering | 15 | Sprint 4 | 12 May 2026 | Open
F-012 | CC6.1-04 | No service account inventory | Medium | CC6 | Service accounts exist in AWS IAM and GitHub; no central inventory or owner mapping. | Build service account inventory with owner, purpose, last-used date; review quarterly. | Security Engineering | 7 | Sprint 3 | 28 April 2026 | Open
F-013 | CC7.1-02 | Vulnerability remediation backlog | Medium | CC7 | 12 High-severity vulnerabilities currently open beyond 30-day SLA. | Close out backlog of 12 overdue Highs before audit period; report SLA compliance monthly. | Security Engineering | 8 | Sprint 1 | 31 March 2026 | Open
F-014 | CC7.3-01 | Incident response tabletop overdue | Medium | CC7 | IR Plan v3.0 (Jan 2025); tabletop exercise overdue (last conducted Sep 2024). | Conduct tabletop exercise within 30 days; schedule semi-annual cadence; retain after-action reports. | CISO | 4 | Sprint 1 | 31 March 2026 | Open
F-015 | CC7.4-01 | No customer communications playbook | Medium | CC7 | Internal comms via Slack #incident-response; external comms ad-hoc. | Document Communications Playbook covering customer, regulator, and media communications by incident type. | CISO / Marketing | 5 | Sprint 3 | 28 April 2026 | Open
F-016 | CC7.5-02 | Backup recovery not recently tested | Medium | CC7 | RDS automated backups in place; full recovery test last performed Aug 2024. | Conduct full recovery test before audit period; document RTO/RPO results; schedule semi-annual cadence. | Platform Engineering | 6 | Sprint 2 | 14 April 2026 | Open
F-017 | CC8.1-05 | Change evidence retention below audit expectation | Medium | CC8 | GitHub PRs and Jira tickets retained 6 months by default; auditor expects 12+ months. | Extend retention of GitHub and Jira data to 24 months minimum; export quarterly to long-term archive. | Engineering | 4 | Sprint 2 | 14 April 2026 | Open
F-018 | CC9.1-01 | BCP not tested in last 12 months | Medium | CC9 | BCP v2.1 documented; not tested in last 12 months. | Conduct BCP exercise (e.g., simulated AWS region failure) within 60 days; document outcomes. | COO / CISO | 6 | Sprint 4 | 12 May 2026 | Open
F-019 | CC9.1-02 | DR cross-region failover untested | Medium | CC9 | DR plan exists; cross-region failover untested at full scale. | Conduct full DR failover test to us-east-1; validate RTO 4hr / RPO 15min; document outcomes. | Platform Engineering | 10 | Sprint 4 | 12 May 2026 | Open
F-020 | CC9.2-02 | No continuous vendor monitoring | Medium | CC9 | Annual reassessment for Tier 1 vendors; no continuous monitoring (e.g., SecurityScorecard). | Implement BitSight or SecurityScorecard for Tier 1 vendors; review monthly; integrate with risk register. | Procurement / CISO | 5 | Sprint 3 | 28 April 2026 | Open
F-021 | CC9.2-07 | Automated retention/deletion not implemented | Medium | CC9 | Retention policy defines 7-year retention for healthcare data; automated deletion not implemented for log data, support tickets, analytics datasets. | Implement automated retention/deletion across log data, customer support tickets, and analytics datasets per Data Retention Standard. | CISO / Platform Engineering | 8 | Sprint 5 | 26 May 2026 | Open
F-022 | CC1.1-01 | Manual training acknowledgement tracking | Low | CC1 | Code of Conduct annual acknowledgement tracked in BambooHR with partial manual export. | Automate acknowledgement evidence export from BambooHR; integrate into Vanta evidence collection. | People & Culture | 3 | Sprint 5 | 26 May 2026 | Open

## 90-Day Roadmap
90-DAY REMEDIATION ROADMAP
6 two-week sprints — sequenced by severity and dependency
Sprint 1 — 29 Apr – 12 May 2026
Theme: Quick wins & High-severity remediation — Close all High findings to remove audit-blocking issues.
ID | Finding | Severity | Owner | Effort (d) | Target Date
F-001 | Incomplete security awareness training & no phishing simulation | High | CISO | 5 | 31 March 2026
F-002 | No defined customer incident notification SLA | High | CISO / General Counsel | 8 | 31 March 2026
F-003 | Annual access reviews fall short of SOC 2 audit expectation | High | CISO / People & Culture | 10 | 31 March 2026
F-004 | No CUEC tracker for sub-service organisations | High | CISO | 6 | 31 March 2026
F-013 | Vulnerability remediation backlog | Medium | Security Engineering | 8 | 31 March 2026
F-014 | Incident response tabletop overdue | Medium | CISO | 4 | 31 March 2026
Sprint total: 6 findings, 41 days effort
Sprint 2 — 13 May – 26 May 2026
Theme: Governance & policies — Refresh stale policies; charter Board oversight; formalise fraud risk.
ID | Finding | Severity | Owner | Effort (d) | Target Date
F-005 | No Board-level Information Security Charter | Medium | CISO / Board Secretary | 4 | 14 April 2026
F-007 | No formal fraud risk assessment | Medium | CFO / CISO | 6 | 14 April 2026
F-009 | Stale policies awaiting review | Medium | CISO | 10 | 14 April 2026
F-016 | Backup recovery not recently tested | Medium | Platform Engineering | 6 | 14 April 2026
F-017 | Change evidence retention below audit expectation | Medium | Engineering | 4 | 14 April 2026
Sprint total: 5 findings, 30 days effort
Sprint 3 — 27 May – 9 Jun 2026
Theme: Process formalisation — Trust Centre, SoD matrix, service account inventory, comms playbook.
ID | Finding | Severity | Owner | Effort (d) | Target Date
F-006 | No customer-facing Trust Centre | Medium | CISO / Marketing | 12 | 28 April 2026
F-010 | Segregation of Duties not formally documented | Medium | CTO / CISO | 5 | 28 April 2026
F-012 | No service account inventory | Medium | Security Engineering | 7 | 28 April 2026
F-015 | No customer communications playbook | Medium | CISO / Marketing | 5 | 28 April 2026
F-020 | No continuous vendor monitoring | Medium | Procurement / CISO | 5 | 28 April 2026
Sprint total: 5 findings, 34 days effort
Sprint 4 — 10 Jun – 23 Jun 2026
Theme: Resilience & PAM — BCP/DR testing, PAM rollout, internal audit engagement.
ID | Finding | Severity | Owner | Effort (d) | Target Date
F-008 | No independent internal audit function | Medium | CISO / Audit Committee | 8 | 12 May 2026
F-011 | No PAM tool for OS-level admin access | Medium | Security Engineering | 15 | 12 May 2026
F-018 | BCP not tested in last 12 months | Medium | COO / CISO | 6 | 12 May 2026
F-019 | DR cross-region failover untested | Medium | Platform Engineering | 10 | 12 May 2026
Sprint total: 4 findings, 39 days effort
Sprint 5 — 24 Jun – 7 Jul 2026
Theme: Data lifecycle & automation — Automated retention/deletion; awareness evidence automation.
ID | Finding | Severity | Owner | Effort (d) | Target Date
F-021 | Automated retention/deletion not implemented | Medium | CISO / Platform Engineering | 8 | 26 May 2026
F-022 | Manual training acknowledgement tracking | Low | People & Culture | 3 | 26 May 2026
Sprint total: 2 findings, 11 days effort
Sprint 6 — 8 Jul – 28 Jul 2026 (final 3 weeks)
Theme: Buffer & audit prep — Buffer for slipped items; auditor pre-meeting; final evidence walkthrough.
ID | Finding | Severity | Owner | Effort (d) | Target Date
Buffer / audit-prep activities only — no new findings scheduled.
Sprint total: 0 findings, 0 days effort

## Effort Summary
EFFORT SUMMARY
BY SEVERITY
Severity | Count | Total Effort (days) | Avg Effort (days)
High | 4 | 29 | 7.25
Medium | 17 | 123 | 7.2353
Low | 1 | 3 | 3
TOTAL | 22 | 155 | 7.0455
BY SPRINT
Sprint | Count | Total Effort (days)
Sprint 1 | 6 | 41
Sprint 2 | 5 | 30
Sprint 3 | 5 | 34
Sprint 4 | 4 | 39
Sprint 5 | 2 | 11
Sprint 6 | 0 | 0
TOTAL | 22 | 155
BY OWNER (TOP CONTRIBUTORS)
Owner | Count | Total Effort (days)
Security Engineering | 3 | 30
CISO | 4 | 25
CISO / Marketing | 2 | 17
Platform Engineering | 2 | 16
CISO / People & Culture | 1 | 10
CISO / General Counsel | 1 | 8
CISO / Audit Committee | 1 | 8
CISO / Platform Engineering | 1 | 8
CFO / CISO | 1 | 6
COO / CISO | 1 | 6
CTO / CISO | 1 | 5
Procurement / CISO | 1 | 5
CISO / Board Secretary | 1 | 4
Engineering | 1 | 4
People & Culture | 1 | 3

## Status Tracker
STATUS TRACKER
Update Status column on the Findings Register sheet; this view auto-recalculates.
OVERALL STATUS
Status | Count | %
Open | 22 | 100%
In Progress | 0 | 0%
Closed | 0 | 0%
REMAINING OPEN BY SEVERITY
Severity | Open Count | Of Total | % Remaining
High | 4 | 4 | 100%
Medium | 17 | 17 | 100%
Low | 1 | 1 | 100%